## ass1
GANTT CHART
PROJECT TITLE |  | European Soccer Database to the team winning percentage/dashboard
PROJECT MANAGER |  | Wesley |  |  |  |  | DATE |  |  | 2020-05-12
WBS NUMBER | TASK TITLE | Sub task | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | WEEK 1 |  | WEEK 2 |  | WEEK 3
[8 empty] | W |  | W |  | W
1 | Product Design
1.1 | Data source |  | 2020-05-12 | 2020-05-20 |  | 100%
1.1.1 | Project theme selection | European Soccer Database to predict the team winning percentage | 2020-05-20 | 2020-05-20 |  | 100%
1.2 | Frame the problem |  | 2020-05-20 | 2020-05-25 |  | 70%
2 | Research
2.1 | state of the art of current problem |  | 2020-05-28 | 2020-05-30 |  | 0%
2.2 | selection of appropriate software tools |  | 2020-05-28 | 2020-05-31 |  | 0%
2.3 | research of methods |  | 2020-05-28 | 2020-06-01 |  | 0%
| approach, algorithms |  | 2020-05-29 | 2020-06-02 |  | 0%
2.4
3 | Written report
3.1 | General description |  | 2020-06-05 |  | 0 | 0%

## ass2
GANTT CHART
PROJECT TITLE |  | Assignment 2 3 |  |  |  |  | COMPANY NAME |  |  | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE |  |  | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [5 empty] | PHASE TWO | [5 empty] | PHASE THREE | [5 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  | WEEK 2 |  | WEEK 3 |  | WEEK 4 |  | WEEK 5 |  | WEEK 6 |  | WEEK 7 |  | WEEK 8 |  | WEEK 9 |  | WEEK 10 |  | WEEK 11 |  | WEEK 12
[8 empty] | W |  | W |  | W |  | W |  | W |  | W |  | W |  | W |  | W |  | W |  | W |  | W
1 | Product Design
1.1 | Data source |  | 2020-05-12 |  |  | 0%
1.1.1 | Project theme selection |  | 2020-05-20 |  |  | 0%
1.2 | Application and requirements analysis |  | 2020-05-20 |  |  | 0%
1.3 | Product functional and non-functional |  | 2020-05-23 |  |  | 0%
1.4 | software architecture design |  | 2020-05-28 |  |  | 0%
1.5 | Guidelines |  | 2020-05-28 |  |  | 0%
1.6 | Project Initiation |  | 2020-05-28 |  |  | 0%
2 | Product Development
2.1 | Scope and Goal Setting |  | 2020-05-28 |  |  | 0%
2.2 | selection of appropriate software tools |  | 2020-05-28 |  |  | 0%
2.3 | Product development software |  | 2020-05-28 |  |  | 0%
2.4 | Risk Management |  | 2020-05-29 |  |  | 0%
3 | Project Management |  |  |  |  | 0%
3.1 | selection of appropriate software tools/platform |  | 2020-06-05 |  | 0 | 0%
3.2 | Product development software |  | 2020-06-05 |  | 0 | 0%
3.2.1 | System testing method |  | 2020-06-05 |  | 0 | 0%
3.2.2 | User evaluation plan and methods |  | 2020-06-12 |  | 0 | 0%
3.3 | Project Updates |  | 2020-06-20 |  | 0 | 0%
3.3.1 | Chart Updates |  | 2020-06-20 |  | 0 | 0%
4 | Project Management |  |  |  |  | 0%
4.1 | Time management with Gantt Chart |  | 2020-06-22 |  | 0 | 0%
4.2 | Risk assessment |  | 2020-06-23 |  | 0 | 0%
4.3 | Quality control on software development |  | 2020-06-24 |  | 0 | 0%
4.4 | Product marketing strategy |  | 2020-06-25 |  | 0 | 0%